## Sheet1
Sunderland Surfacing Programme 20/21 |  |  | 7pm to 6am Closure | 8am to 6pm Closure
Issue 1 - 12/05/20 |  | Page 1 | 9:30am to 3pm Temp Signals | 9:30am to 3pm Closure
|  | Hand Lay | Planing | Surfacing | Ward
Saturday | 2020-05-30 |  | A183 Chester Road, Pennywell Eastbound | A183 Chester Road, Pennywell Eastbound | St Annes
Sunday | 2020-05-31 |  | A183 Chester Road, Pennywell Eastbound | A183 Chester Road, Pennywell Eastbound | St Annes
Monday | 2020-06-01 | A183 Chester Road, Pennywell | A183 Chester Road, Pennywell Eastbound | A183 Chester Road, Pennywell Eastbound | St Annes
Tuesday | 2020-06-02 |  | A183 Chester Road, Pennywell Westbound | A183 Chester Road, Pennywell Westbound | Sandhill
Wednesday | 2020-06-03 | A183 Chester Road, Pennywell | A183 Chester Road, Pennywell Westbound | A183 Chester Road, Pennywell Westbound | Sandhill
Thursday | 2020-06-04 | Chestergate Housing Development | Chestergate Housing Development | Chestergate Housing Development | St Annes
Friday | 2020-06-05 | Chestergate Housing Development | Chestergate Housing Development | Chestergate Housing Development | St Annes
Saturday | 2020-06-06
Sunday | 2020-06-07 | C511 Hylton Road | C511 Hylton Road | C511 Hylton Road | Millfield
Monday | 2020-06-08 | IAMP | IAMP | IAMP
Tuesday | 2020-06-09 | IAMP | IAMP | IAMP
Wednesday | 2020-06-10 | IAMP | IAMP | IAMP
Thursday | 2020-06-11 | IAMP | IAMP | IAMP
Friday | 2020-06-12 | IAMP | IAMP | IAMP
Saturday | 2020-06-13
Sunday | 2020-06-14 | C511 Hylton Road PH4 |  | C511 Hylton Road Phase 4 | Millfield
Monday | 2020-06-15 |  | Rye View Road | Rye View Road | Ryhope
Tuesday | 2020-06-16 | Rye View Road |  | Rye View Road | Ryhope
Wednesday | 2020-06-17 | St Lukes Road | St Lukes Road | St Lukes Road | St Annes
Thursday | 2020-06-18 |  | Langdale Road Phase 3 | Langdale Road Phase 3 | Shiney Row
Friday | 2020-06-19 | Langdale Road Phase 3 |  | Langdale Road Phase 3 | Shiney Row
Saturday | 2020-06-20
Sunday | 2020-06-21 | A183 Chester Road, Nookside | A183 Chester Road, Nookside | A183 Chester Road, Nookside | St Annes
Monday | 2020-06-22 |  | Stone Cellar Road - Phase 2 (Silloth Drive to west) | Stone Cellar Road - Phase 2 (Silloth Drive to west) | Washington West
Tuesday | 2020-06-23 | Stone Cellar Road - Phase 2 (Silloth Drive to west) |  | Stone Cellar Road - Phase 2 (Silloth Drive to west) | Washington West
Wednesday | 2020-06-24 |  | C502 Bonemill Lane Eastbound | C502 Bonemill Lane Eastbound | Washington West
Thursday | 2020-06-25 | C502 Bonemill Lane Eastbound |  | C502 Bonemill Lane Eastbound | Washington West
Friday | 2020-06-26 |  | Albany Way | Albany Way | Washington North / Washington West
Saturday | 2020-06-27
Sunday | 2020-06-28 | B1522 Ryhope Road (Ocean Road) | B1522 Ryhope Road (Ocean Road) | B1522 Ryhope Road (Ocean Road) | Ryhope
Monday | 2020-06-29 | Albany Way |  | Albany Way | Washington North / Washington West
Tuesday | 2020-06-30 |  | B1405 Springwell Road | B1405 Springwell Road | Barnes
Wednesday | 2020-07-01 | B1405 Springwell Road | Tunstall Hope Road | B1405 Springwell Road | Barnes
Thursday | 2020-07-02 |  | Paddock Lane | Tunstall Hope Road | Doxford/Ryhope/Silksworth
Friday | 2020-07-03 | Paddock Lane |  | Paddock Lane | Doxford/Ryhope
Sunderland Surfacing Programme 20/21 |  |  | 7pm to 6am Closure | 8am to 6pm Closure
Issue 1 - 12/05/20 |  | Page 2 | 9:30am to 3pm Temp Signals | 9:30am to 3pm Closure
|  | Hand Lay | Planing | Surfacing
Saturday | 2020-07-04
Sunday | 2020-07-05 | B1522 Ryhope Road (Ocean Road) | B1522 Ryhope Road (Ocean Road) | B1522 Ryhope Road (Ocean Road) | Ryhope
Monday | 2020-07-06 |  | Moorside Road | Moorside Road | Doxford
Tuesday | 2020-07-07 | Moorside Road |  | Moorside Road | Doxford
Wednesday | 2020-07-08 |  | Glanville Road | Glanville Road | Doxford
Thursday | 2020-07-09 | Glanville Road | Elmwood Avenue | Glanville Road | Doxford
Friday | 2020-07-10 | Elmwood Avenue |  | Elmwood Avenue | Southwick
Saturday | 2020-07-11
Sunday | 2020-07-12 |  | A182 Newbottle Street | A182 Newbottle Street | Copt Hill
Monday | 2020-07-13 |  | Toward Road, Phase 1 | Toward Road, Phase 1 | Hendon
Tuesday | 2020-07-14 | Toward Road, Phase 1 |  | Toward Road, Phase 1 | Hendon
Wednesday | 2020-07-15 | Toward Road, Phase 2 | Toward Road, Phase 2 | Toward Road, Phase 2 | Hendon
Thursday | 2020-07-16 |  | Toll Bar Road | Toll Bar Road | Ryhope
Friday | 2020-07-17 | Toll Bar Road |  | Toll Bar Road | Ryhope
Saturday | 2020-07-18
Sunday | 2020-07-19 | A182 Newbottle Street |  | A182 Newbottle Street | Copt Hill
Monday | 2020-07-20 | A1231 Sunderland Highway WB | A1231 Sunderland Highway WB | A1231 Sunderland Highway WB | Washington East
Tuesday | 2020-07-21 | Fawcett Street | Fawcett Street | Fawcett Street | Millfield/Hendon
Wednesday | 2020-07-22 | Burdon Road | Burdon Road | Burdon Road | Doxford
Thursday | 2020-07-23 |  | B1287 Sea View(Coast Road) | B1287 Sea View(Coast Road) | Ryhope
Friday | 2020-07-24 | B1287 Sea View(Coast Road) |  | B1287 Sea View(Coast Road) | Ryhope
Saturday | 2020-07-25
Sunday | 2020-07-26 |  | C511 Hylton Road PH5 | C511 Hylton Road PH5 | Millfield
Monday | 2020-07-27 |  | A1231 /A195 Interchange Eastbound | A1231 /A195 Interchange Eastbound | Washington North
Tuesday | 2020-07-28 | A1231 /A195 Interchange Eastbound |  | A1231 /A195 Interchange Eastbound | Washington North
Wednesday | 2020-07-29 |  | Sedling Road | Sedling Road | Washington South
Thursday | 2020-07-30 | Sedling Road |  | Sedling Road | Washington South
Friday | 2020-07-31
Saturday | 2020-08-01
Sunday | 2020-08-02 |  | C511 Hylton Road PH5 | C511 Hylton Road PH5 | Millfield